PNG National Service Delivery and Trends Assessment

Project Overview

The National Service Delivery and Trends Assessment (NSDTA), to be implemented in 2025, is a large-scale survey of service provision that will investigate service delivery at the sub-national level in 34 Districts across Papua New Guinea (PNG) and in the Autonomous Region of Bougainville (ARoB). It is the successor to the groundbreaking Public Expenditure and Service Delivery (PESD) study of 2002, conducted by PNG’s National Research Institute (NRI) and the World Bank, and the Promoting Effective Public Expenditure (PEPE) study of 2012, conducted by the NRI and the Australian National University. Building on this earlier work, the nationally representative NSDTA will provide a deep understanding of how public financing, governance and service delivery currently work in practice across PNG.

By tracing national budgetary allocations to provincial and district levels, and then to front-line facilities, the research will offer critical insights into where public financing succeeds, or fails, to deliver basic services to Papua New Guinean communities. Importantly it will provide trend data on the state of health and education services across the country, and insights into the impact of policy and financing reforms in both the sectors. In addition, it will provide for the first time, similar data on the law and justice sector. In doing so it responds to the PNG Government’s acknowledged need for “reliable and timely data across all levels of Government” and its call for “Development Partner programs to be coordinated with the MTDP Framework for greater sector outcomes” (See: Medium term Development Plan IV 2023-2027:68).

Designed to support PNG’s policy priorities and its development agenda by delivering robust and difficult-to-source panel data to support informed decision-making and evidence-based planning, the NSDTA has four overall objectives, namely:

- To analyse the impact of major PNG Government expenditure reforms, assess the success or otherwise of those reforms in translating budget allocations into effective service delivery performance, and to understand the reasons for their success or failure;

- To make service delivery performance data available to PNG’s political and bureaucratic leadership, donors, civil society and general public in order to promote more effective and more transparent budget allocations and expenditure practices;

- To build the research and analytical capacity of PNG-based researchers individually and at the institutional level; and

- To provide high quality data on the condition, funding availability and services performed by primary schools, primary healthcare facilities and sub-national law and justice services across the country.

Its outputs will be relevant to government stakeholders at all levels - national, provincial, district and local level – and to donors, civil society and others working to improve service delivery performance in PNG.

The NSDTA research team and funding arrangements

Led by the ANU Department of Pacific Affairs (DPA), and implemented through the Pacific Research Program, the NSDTA is funded by the Australian government through the Department of Foreign Affairs and Trade, with co-funding from the ANU. It principally involves a collaboration between DPA and the NRI and builds on established institutional arrangements, including our partnership under the previous iteration of the study in 2012. Other research partners involved in delivering the NSDTA include the University of Papua New Guinea, the University of New South Wales in Australia, and the World Bank.

Designed to build local research capacity and to support the development of a network of public expenditure specialists and local researchers, the NSDTA will involve 50 locally engaged researchers, and will see five research teams, each led by an experienced PNG researcher deployed throughout PNG. To ensure smooth running of the project, a PNG-based managing contractor will support the field research, assisting with logistics and security.

Governance and implementation of the NSDTA

Two committees made up of crucial stakeholders will be established at the outset of the project – these being the project’s Steering Committee, which will meet twice a year during the life of the project, and an Implementing Partners and Stakeholder Advisory Committee, that will meet quarterly.

The NSDTA will begin in February 2025, with a series of stakeholder consultations in Port Moresby, after which the first Steering Committee and Implementing Partners and Stakeholder Advisory Committee meetings will be convened. Acting Deputy Secretary, Chrisopher Asa, who heads the Department of Prime Minister and National Executive Council’s Policy Coordination and Monitoring Division II which carries responsibility for the Law and Justice, Governance, and Social Sectors and for Administrative, Provincial and District Services has agreed to sit on the project steering committee and will receive regular project updates.

The project team expects to pilot the research instruments at the start of the second quarter, with the main period of fieldwork to occur between July to December 2025. Data analysis will be carried out between January and June 2026, with preliminary findings issued in June 2026. A final report will be published no later than December 2026.

The previously utilised sampling framework comprising eight provinces and a pilot in PNG’s National Capital District, has been expanded to include Western Province and ARoB. It will see fieldwork undertaken in NCD, ARoB and nine provinces, namely: East New Britain and West New Britain (New Guinea Islands Region), Morobe and Sandaun (Momase Region), Western Highlands, Enga and Eastern Highlands (Highlands Region), and in Gulf and Western provinces (Southern Region). In total the NSDTA will see 34 of PNG’s 96 districts surveyed.